## UAT
User Acceptance Test Plan
Project Name |  | Agile Project – Smart watch E-commerce site
Project Client |  | EIT
Name of Tester/s: |  | Euan, Zaine, Austin
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
COMPONENT/MODULE 1: |  | Navigation & links
1 | Home page product showcase | 1. Load home page. 2. Scroll to 'Latest Watches' section. 3. Verify product grid matches "Watches" page. 4. Verify view all link works. | https://zainjohn.github.io/Agile-Projects/ | Home page displays same 7 products in identical layout. 'View All' link is present and navigates to products page. | Home page displays same 7 products in an identical layout. "View All" link is present but does not navigate to "Watches" page. | Fail | "View All" link did not redirect user to "Watches" page
2 | Navigation Bar | 1. Load each page from the naviagtion bar. 2. Verify each page loads correctly. 3. Verify Nav bar is identical across pages. | https://zainjohn.github.io/Agile-Projects/ | Each page loads after clicking the link. Nav bar remains identical between pages | Each page loads and displays the correct information and the nav bar is the same on all pages. | Pass
3 | Footer Information | 1. Scroll to the footer 2. Verify footer contains contact information and social media links 3. Verify footer is identical between pages. | https://zainjohn.github.io/Agile-Projects/ | Footer contains contact information and social media links Footer stays constistant between pages. | The footer contains the contact information and social media link across all pages | Pass
4
COMPONENT/MODULE 2: |  | Custom Plugin Functionality
1 | Contact form presence | 1. Navigate to Contact page. 2. Verify form fields: Full Name, Email, Phone number, Message. 3. Verify SEND button. | https://zainjohn.github.io/Agile-Projects/contact.html | Contact form contains 4 input fields (Full Name, Email, Phone number, Message) and a SEND button. Form should have correct data validation e.g 'email must contain @' | Contact form contains all 4 input fields and a send button. The email field has working data validation however the phone number field does not. | Fail | "Phone Number" field in Contact form should have working data validation.
2
3
4
5
COMPONENT/MODULE 3: |  | UI & UX
1 | Orders page – Order history & summary
2 | Contact form presence
3
4
5